## Master Plan — Play
TDC /play Pillar — Enjoy + Fit Merged ¦ Database + JSX Build Plan
Enjoy = outings, parks, playdates, events. Fit = walking, running, swimming, agility, training. Same parent intent → /play
WHY ENJOY + FIT = PLAY
Signal | Enjoy | Fit | Merged /play
Parent intent | Fun with my dog outside | Keep my dog healthy & active | The same trip to the park does both
User journey | Plan a park day → playdate | Book a walk → track fitness | Play, run, swim, explore — one page
Product overlap | Cooling vest, bandana | Cooling vest, agility set | Same products surface for both
Service overlap | Park discovery, weekend plan | Dog walking, outdoor sessions | Same Concierge handles both
Nav clarity | 14 items | — | Reduces to 9 cleaner items
CURRENT DATA STATE
Asset | Enjoy | Fit | Total | Quality | Action
Services (raw) | 28 | 78 | 106 | High junk in Fit (training, passports, products) | CLEAN → 8+8 canonical
Bookable services | 5 | 13 | 18 | Good core — these stay | KEEP all bookable
Products tagged play | 67 | 0 | 67 | 33 bandanas + 33 playdate cards | SET pillar=play
Fit products (0 in DB) | 0 | 0 | 0 | Nothing exists yet | ADD 25 new products
Bundles | 0 | 1 (incomplete) | 1 | No real play/fit bundles | CREATE 14 bundles
Soul products | 33 bandanas + 33 cards | 0 | 66 | Already in DB — just untagged | 2× updateMany()
PLAY PAGE STRUCTURE — 7 FILES
File | Location | Lines ~ | Mirrors | Key Function | Route
PlaySoulPage.jsx | /pages/ | ~1,700 | GoSoulPage.jsx | Main page: ActivityProfile, MiraPicksSection, 8 flows, PlayConcierge | <Route path='/play' element={<PlaySoulPage/>}/>
PlayHero.jsx | /components/play/ | ~120 | GoHero.jsx | Vibrant green hero, activity chips | import PlayHero
PlayCategoryStrip.jsx | /components/play/ | ~40 | GoCategoryStrip.jsx | 6 dimension pills | import PlayCategoryStrip
GuidedPlayPaths.jsx | /components/play/ | ~420 | GuidedGoPaths.jsx | 6 play paths with 4-step flow | import GuidedPlayPaths
PlayConciergeSection.jsx | /components/play/ | ~80 | GoConciergeSection.jsx | 'Play, Personally' section | import PlayConciergeSection
PlayConciergeModal.jsx | /components/play/ | ~150 | GoConciergeModal.jsx | 3-question intake → POST /api/concierge/play-intake | import PlayConciergeModal
PLAY DIMENSIONS (6)
Dimension | ID | Badge | Glow | Mira logic | API category
Outings & Parks | outings | Explore | TRUE | Location + breed energy level | Play Essentials
Playdates | playdates | Social | TRUE | Breed + other pets flag | Play Essentials
Dog Walking | walking | Daily | TRUE | Size + energy + age | Play Essentials
Fitness & Training | fitness | Active | TRUE | Weight + health condition | Fitness & Training
Swimming & Hydro | swimming | Cools down | TRUE | Coat type + joint health | Fitness & Training
Soul Play | soul | Made for you | TRUE | Breed bandana + playdate card | Soul Play Products

## Enjoy Services (28 → 8)
Enjoy Services — Clean 28 → 8 Canonical ¦ After merge: SET pillar='play' on all 8 green rows
Service ID | Service Name | Price | Bookable | Canonical Flow | JSX Flow ID | Watercolour Prompt | Decision | Action
SVC-ENJOY-PARKS | Pet Parks Discovery | Free | Yes | parks — Park & Playdate flow | parks | Watercolour: a joyful dog running free in a sunlit park, green grass, warm sunlight, 16:9 | 🟢 KEEP | Primary — park finder entry point
SVC-ENJOY-PLAYDATE | Playdate Coordination | ₹300 | Yes | playdates — Park & Playdate flow | parks | Watercolour: two dogs playing together joyfully in a park, warm afternoon light, 16:9 | 🟢 KEEP | Primary — playdate booking
SVC-ENJOY-EVENTS | Pet Events & Experiences | ₹500 | Yes | events — Weekend Outing flow | weekend | Watercolour: a happy crowd of dogs and owners at a pet festival, colourful bunting, 16:9 | 🟢 KEEP | Primary — event booking
SVC-ENJOY-SOCIAL | Socialisation Planning | ₹800 | Yes | social — Park & Playdate flow | parks | Watercolour: a puppy meeting other dogs in a structured socialisation class, warm green tones, 16:9 | 🟢 KEEP | Primary — socialisation planning
SVC-ENJOY-WEEKEND | Weekend Outing Planning | ₹400 | Yes | weekend — Weekend Outing flow | weekend | Watercolour: a family and dog on a weekend adventure, golden afternoon light, 16:9 | 🟢 KEEP | Primary — weekend planning
svc-community-81fae822 | Breed-Specific Playdate | Free | No | playdates — Park & Playdate flow | parks | Watercolour: same-breed dogs playing together, joyful and breed-specific, warm park setting, 16:9 | 🟢 KEEP | Good concept — make bookable
svc-enjoy-eabfa586 | Dog Beach Day | Free | No | weekend — Weekend Outing flow | weekend | Watercolour: a dog running on a sunny beach, waves and golden sand, joyful, 16:9 | 🟢 KEEP | Good — make bookable
svc-svc-enjoy-a8ba8999 | Social Calendar Management | Free | No | social — Park & Playdate flow | parks | Watercolour: a beautiful illustrated social calendar with paw prints and park days, 16:9 | 🟢 KEEP | Good — Mira manages the social life
svc-community-96d0306f | Pet-Friendly Event Ticket | Free | No | events (MERGE into Pet Events) | — | — | 🟡 MERGE | Duplicate of Pet Events & Experiences
svc-care-4c49bf18 | Heartworm Prevention | Free | No | WRONG PILLAR — move to /care | — | — | 🔴 MOVE | This is a care service — not play
svc-PROD-F19DE643DFD0 | Social Butterfly Bandana | Free | No | PRODUCT not service — move to products | — | — | 🔴 MOVE | This is a product — delete from services
svc-PROD-3ED36187B10C | Cooling Vest for Outdoor Fun | Free | No | PRODUCT not service — move to products | — | — | 🔴 MOVE | This is a product — delete from services
svc-PROD-1E8FFC699847 | Social Profile Tag | Free | No | PRODUCT not service — move to products | — | — | 🔴 MOVE | This is a product — delete from services
svc-dine-picnic | Gourmet Picnic Setup | Free | No | weekend (MERGE into Weekend Outing) | — | — | 🟡 MERGE | Merge into Weekend Outing Planning
svc-dine-group-event | Group Dining Events | Free | No | events (MERGE into Pet Events) | — | — | 🟡 MERGE | Better fit in /dine — move there
svc-care-1377d639 | Flea & Tick Prevention | Free | No | WRONG PILLAR — move to /care | — | — | 🔴 MOVE | Care service — not play
svc-community-6898a12a | Dog Park Meetup Pass (Monthly) | Free | No | parks (MERGE into Pet Parks Discovery) | — | — | 🟡 MERGE | Merge as monthly pass tier
svc-community-6771dc01 | Pet Parent Social Club Membership | Free | No | social (MERGE into Social Calendar) | — | — | 🟡 MERGE | Merge into Social Calendar Management
svc-svc-enjoy-a2f999b2 | Adventure Day Out | Free | No | weekend (MERGE into Weekend Outing) | — | — | 🟡 MERGE | Merge into Weekend Outing Planning
svc-PROD-CAECA555999E | Event Day Backpack | Free | No | PRODUCT — move to products | — | — | 🔴 MOVE | Product not service
svc-enjoy-efd5110c | Dog Park Meetup Pass | Free | No | parks (MERGE — duplicate) | — | — | 🟡 MERGE | Duplicate of monthly pass
svc-dine-d6cfc31d | Puppy Picnic Set | Free | No | PRODUCT — move to products | — | — | 🔴 MOVE | Product not service
svc-seed-care-3e3213a3 | Flea & Tick Prevention Pack | Free | No | WRONG PILLAR — move to /care | — | — | 🔴 MOVE | Care — not play
svc-seed-enjoy-d9d90d4 | Dog Park Playdate Booking | Free | No | parks (MERGE — duplicate of Playdate) | — | — | 🟡 MERGE | Duplicate
svc-svc-enjoy-57ba0150 | Playdate Coordination Service | Free | No | parks (MERGE — duplicate) | — | — | 🟡 MERGE | Duplicate of Playdate Coordination
svc-PROD-B19A48A8F5F8 | Dog Park Day Pass | Free | No | parks (MERGE — product/pass) | — | — | 🟡 MERGE | Merge as day pass option
svc-PROD-6662F741F7C7 | Paws & Play Delhi | Free | No | parks (MERGE — venue listing) | — | — | 🟡 MERGE | Venue listing — add to PetFriendlyPlaces
svc-PROD-750BE03D6799 | Beach Day Experience | Free | No | weekend (MERGE into Beach Day) | — | — | 🟡 MERGE | Merge into Dog Beach Day
8 canonical (green). 12 to merge (yellow). 8 to move to correct pillar (red — Heartworm/Flea→care, products→remove from services).
DB COMMAND — run after merging enjoy services to 8 canonical:
db.services.updateMany( {_id:{$in:[/*IDs of 8 canonical enjoy services*/]}}, {$set:{pillar:'play',category:'enjoy'}} ) — OR by name: {name:{$in:['Pet Parks Discovery','Playdate Coordination','Pet Events & Experiences','Socialisation Planning','Weekend Outing Planning','Breed-Specific Playdate','Dog Beach Day','Social Calendar Management']}}

## Fit Services (78 → 8)
Fit Services — Clean 78 → 8 Canonical ¦ After merge: SET pillar='play' on all 8 green rows
Service ID | Service Name | Price | Bookable | Canonical Flow | JSX Flow ID | Watercolour Prompt | Decision | Action
SVC-FIT-WALK-DAILY | Dog Walking — Daily | ₹300 | Yes | walking — Dog Walking flow | walking | Watercolour: a professional dog walker and happy dog on a sunny morning walk, green park, 16:9 | 🟢 KEEP | Primary
SVC-FIT-WALK-MONTHLY | Dog Walking — Monthly Package | ₹6000 | Yes | walking — Dog Walking flow | walking | Watercolour: a dog walker with multiple dogs in a park, warm sunlight, joyful energy, 16:9 | 🟢 KEEP | Primary
svc-fit-assessment | Fitness Assessment & Programme Design | ₹999 | Yes | fitness — Fitness Assessment flow | fitness | Watercolour: a professional assessing a dog's fitness with gentle movement in a bright garden, 16:9 | 🟢 KEEP | Primary
SVC-FIT-WEIGHT | Weight Management Program | ₹2500 | Yes | fitness — Fitness Assessment flow | fitness | Watercolour: a healthy active dog running, bright energetic colours, weight loss journey, 16:9 | 🟢 KEEP | Primary
SVC-FIT-SWIM | Swimming Sessions | ₹1000 | Yes | swimming — Swimming flow | swimming | Watercolour: a happy dog swimming in a pool or lake, splashing water, joyful energy, 16:9 | 🟢 KEEP | Primary
svc-fit-hydro | Hydrotherapy Sessions | Free | No | swimming — Swimming flow | swimming | Watercolour: a dog in a hydrotherapy pool with gentle support, therapeutic and warm, 16:9 | 🟢 KEEP | Make bookable
SVC-FIT-SENIOR | Senior Mobility Planning | ₹1200 | Yes | fitness — Fitness Assessment flow | fitness | Watercolour: a gentle senior dog doing low-impact movement in a sunlit garden, soft warm tones, 16:9 | 🟢 KEEP | Primary
svc-fit-agility | Agility Foundation Course | Free | No | fitness — Fitness & Training flow | fitness | Watercolour: a dog joyfully running through an agility course with colourful obstacles, 16:9 | 🟢 KEEP | Make bookable
svc-fit-training | Personal Training Programme - 8 Weeks | Free | No | fitness (MERGE → Fitness Assessment) | — | — | 🟡 MERGE | Merge as premium tier of Fitness Assessment
svc-fit-weight | Weight Management Programme | Free | No | fitness (MERGE → Weight Management duplicate) | — | — | 🟡 MERGE | Duplicate of SVC-FIT-WEIGHT — delete
svc-fit-senior | Senior Mobility Programme | Free | No | fitness (MERGE → Senior Mobility duplicate) | — | — | 🟡 MERGE | Duplicate of SVC-FIT-SENIOR — delete
svc-fit-puppy | Puppy Development Programme | Free | No | fitness (MERGE → Fitness Assessment, puppy flag) | — | — | 🟡 MERGE | Add puppy_stage flag to Fitness Assessment
svc-fit-yoga | Canine Yoga (Doga) Session | Free | No | swimming (MERGE → add to Swimming flow) | — | — | 🟡 MERGE | Add as yoga option in Swimming/Movement flow
SVC-FIT-ACTIVITY | Breed-Appropriate Activity Plan | ₹1000 | Yes | fitness (MERGE → Fitness Assessment premium) | — | — | 🟡 MERGE | Merge as add-on to Fitness Assessment
SVC-FIT-INDOOR | Indoor Exercise Routines | ₹800 | Yes | fitness (MERGE → part of Fitness Assessment) | — | — | 🟡 MERGE | Merge as indoor variant
SVC-FIT-OUTDOOR | Outdoor Exercise Sessions | ₹500 | Yes | walking (MERGE → Dog Walking outdoor variant) | — | — | 🟡 MERGE | Merge as outdoor add-on to Dog Walking
svc-fit-swimming | Swimming Session | ₹999 | Yes | swimming (MERGE → duplicate of Swimming Sessions) | — | — | 🟡 MERGE | Duplicate — delete, keep SVC-FIT-SWIM
svc-fit-hydrotherapy | Hydrotherapy | ₹1499 | Yes | swimming (MERGE → duplicate of Hydrotherapy) | — | — | 🟡 MERGE | Duplicate of svc-fit-hydro — merge price
svc-fit-fitness-assess | Fitness Assessment | ₹799 | Yes | fitness (MERGE → duplicate of Assessment) | — | — | 🟡 MERGE | Duplicate of svc-fit-assessment — delete
svc-fit-dog-walking | Professional Dog Walking | ₹399 | Yes | walking (MERGE → duplicate of Daily Walk) | — | — | 🟡 MERGE | Duplicate of SVC-FIT-WALK-DAILY — delete
svc-learn-f285fc00 | Advanced Commands Training | Free | No | WRONG PILLAR → /learn | — | — | 🔴 MOVE | Training commands → /learn pillar
svc-learn-332dfec9 | Service Dog Training | Free | No | WRONG PILLAR → /learn | — | — | 🔴 MOVE | Service dog training → /learn pillar
svc-learn-4781e95d | Recall Training Intensive | Free | No | WRONG PILLAR → /learn | — | — | 🔴 MOVE | Recall training → /learn pillar
svc-paperwork-9c3cb546 | Pet Passport Application Service | Free | No | WRONG PILLAR → /know | — | — | 🔴 MOVE | Paperwork → /know pillar
svc-travel-14fe2322 | Pet Passport Service | Free | No | WRONG PILLAR → /know or /go | — | — | 🔴 MOVE | Travel docs → /go or /know pillar
svc-emergency-27c8523d | Emergency Transport Service | Free | No | WRONG PILLAR → /emergency | — | — | 🔴 MOVE | Emergency → /emergency pillar
svc-seed-emergency-0fb | First Aid Training Workshop | Free | No | WRONG PILLAR → /learn or /emergency | — | — | 🔴 MOVE | First aid → /emergency or /know
svc-emergency-84b8d7ec | First Aid Training Course | Free | No | WRONG PILLAR → /emergency | — | — | 🔴 MOVE | First aid → /emergency pillar
svc-learn-2e9e8ba7 | House Training Program | Free | No | WRONG PILLAR → /learn | — | — | 🔴 MOVE | House training → /learn pillar
svc-learn-d28a0927 | Online Training Course | Free | No | WRONG PILLAR → /learn | — | — | 🔴 MOVE | Online training → /learn pillar
svc-learn-9f57f471 | Private In-Home Training Session | Free | No | WRONG PILLAR → /learn | — | — | 🔴 MOVE | In-home training → /learn pillar
svc-learn-f64be77d | Private Training Session | Free | No | WRONG PILLAR → /learn | — | — | 🔴 MOVE | Private training → /learn pillar
svc-advisory-4bcf8a7b | Training Method Consult | Free | No | WRONG PILLAR → /know | — | — | 🔴 MOVE | Advisory → /know pillar
svc-PROD-D47FAB5ABD8B | Cooling Exercise Vest | Free | No | PRODUCT — remove from services | — | — | 🔴 MOVE | Product not service
svc-PROD-79B99C9EAE9F | Pet Weight Management Scale | Free | No | PRODUCT — remove from services | — | — | 🔴 MOVE | Product not service
svc-PROD-A938A011CBB1 | Pet Weight Scale | Free | No | PRODUCT — duplicate — remove | — | — | 🔴 MOVE | Duplicate product
svc-PROD-B04D6E0B0E54 | Agility Training Set | Free | No | PRODUCT — remove from services | — | — | 🔴 MOVE | Product not service
svc-learn_prod_clicker | Professional Training Clicker | Free | No | PRODUCT — remove from services | — | — | 🔴 MOVE | Product not service
svc-697dbae5572fc2185d | Exercise Ball Launcher | Free | No | PRODUCT — remove from services | — | — | 🔴 MOVE | Product not service
svc-fit-product-122b5f | Weighted Exercise Vest | Free | No | PRODUCT — remove from services | — | — | 🔴 MOVE | Product not service
svc-697dbae5572fc2185d | Weighted Vest for Dogs | Free | No | PRODUCT — duplicate — remove | — | — | 🔴 MOVE | Product duplicate
svc-travel-prod-a9ec81 | Pet Passport Holder | Free | No | PRODUCT → /go pillar products | — | — | 🔴 MOVE | Go product not play service
svc-enjoy-c2ccdd9c | Hiking Trail Pass | Free | No | walking (MERGE → Weekend Outing as hiking add-on) | — | — | 🟡 MERGE | Merge as hiking option
svc-enjoy-edad76f0 | Sunrise Dog Walk | Free | No | walking (MERGE → Dog Walking early morning) | — | — | 🟡 MERGE | Merge as early-morning walk variant
svc-fit-de7330a4 | Sprint Training Session | Free | No | fitness (MERGE → Fitness Assessment high-energy) | — | — | 🟡 MERGE | Add as high-energy breed option
svc-fit-20c869ef | Personal Fitness Assessment | Free | No | fitness (MERGE → duplicate of Assessment) | — | — | 🟡 MERGE | Duplicate — delete
svc-fit-0706f65f | Swimming Therapy Session | Free | Yes | swimming (MERGE → Hydrotherapy) | — | — | 🟡 MERGE | Therapeutic variant — merge into Hydrotherapy
svc-bundle-fit-transfo | Complete Fitness Transformation | Free | No | fitness (MERGE → Fitness Assessment premium) | — | — | 🟡 MERGE | Bundle/premium tier — merge
svc-enjoy-2307e263 | Doggy Swimming Session | Free | Yes | swimming (MERGE → duplicate) | — | — | 🟡 MERGE | Duplicate of Swimming Sessions
svc-enjoy-c4374ad1 | Doggy Yoga Session | Free | Yes | swimming (MERGE → Yoga/movement variant) | — | — | 🟡 MERGE | Yoga variant — merge into Swimming/Movement
svc-fit-da240769 | Hydrotherapy Session | Free | Yes | swimming (MERGE → third duplicate) | — | — | 🟡 MERGE | Third hydrotherapy duplicate — delete
svc-fit-e863d305 | Balance Ball Training | Free | No | fitness (MERGE → Fitness Assessment add-on) | — | — | 🟡 MERGE | Balance training add-on
svc-fit-cd0415bd | Agility Training Sessions (4 Pack) | Free | No | fitness (MERGE → Agility Foundation Course) | — | — | 🟡 MERGE | Pack variant — merge with price
svc-seed-enjoy-dd8937e | Swimming Pool Session | Free | Yes | swimming (MERGE → duplicate) | — | — | 🟡 MERGE | Duplicate
svc-seed-fit-9fbbea2b | Personal Training Session | Free | No | fitness (MERGE → duplicate) | — | — | 🟡 MERGE | Duplicate
svc-seed-fit-ce084921 | Puppy Fitness Starter | Free | No | fitness (MERGE → Fitness Assessment puppy) | — | — | 🟡 MERGE | Puppy variant
svc-svc-enjoy-aabd3519 | Swimming Session - Pool | Free | Yes | swimming (MERGE → duplicate) | — | — | 🟡 MERGE | Duplicate
svc-svc-learn-dd8da108 | Private Training - Home Visit | Free | No | WRONG PILLAR → /learn | — | — | 🔴 MOVE | Learning → /learn
svc-fit-9a00b7ab | Dog Running Session | Free | Yes | walking (MERGE → Dog Walking running variant) | — | — | 🟡 MERGE | Running variant of walking
svc-fit-5a3d45ff | Agility Training Session | Free | Yes | fitness (MERGE → Agility Foundation duplicate) | — | — | 🟡 MERGE | Duplicate
svc-seed-enjoy-53d3897 | Agility Course Access | Free | No | fitness (MERGE → Agility Foundation) | — | — | 🟡 MERGE | Venue access — merge
svc-seed-fit-6e3038cf | Weight Loss Program (4 Weeks) | Free | No | fitness (MERGE → Weight Management) | — | — | 🟡 MERGE | 4-week variant — merge with duration flag
svc-seed-fit-92c2a48f | Swimming Fitness Class | Free | No | swimming (MERGE → duplicate) | — | — | 🟡 MERGE | Duplicate
svc-seed-fit-dc3c3a43 | Monthly Fitness Subscription | Free | No | fitness (MERGE → Fitness Assessment monthly) | — | — | 🟡 MERGE | Subscription variant
svc-seed-fit-0f7980a3 | Agility Training Course | Free | No | fitness (MERGE → Agility duplicate) | — | — | 🟡 MERGE | Duplicate
svc-seed-learn-02b0a36 | Advanced Training Program | Free | No | WRONG PILLAR → /learn | — | — | 🔴 MOVE | Training → /learn
svc-fit-program | Personal Training Program | Free | No | fitness (MERGE → duplicate) | — | — | 🟡 MERGE | Duplicate
svc-fit-773d1514 | Treadmill Training | Free | No | fitness (MERGE → Fitness Assessment indoor) | — | — | 🟡 MERGE | Indoor variant
svc-fit-196b6fe2 | Monthly Fitness Plan | Free | No | fitness (MERGE → duplicate of subscription) | — | — | 🟡 MERGE | Duplicate
svc-seed-fit-bfc542fb | Canine Treadmill Session | Free | Yes | fitness (MERGE → Treadmill Training) | — | — | 🟡 MERGE | Duplicate of Treadmill Training
svc-seed-fit-a62e3b62 | Dog Yoga (Doga) Session | Free | Yes | swimming (MERGE → Yoga variant) | — | — | 🟡 MERGE | Third yoga duplicate
svc-fit-assessment | Fitness Assessment | Free | Yes | fitness (MERGE → duplicate canonical) | — | — | 🟡 MERGE | Duplicate — keep svc-fit-assessment
svc-fit-hydro | Hydrotherapy | Free | No | swimming (MERGE → duplicate) | — | — | 🟡 MERGE | Handled above
83efaae5 | Scent Dog Nose Work Training | Free | No | fitness (MERGE → Mental Exercise add-on) | — | — | 🟡 MERGE | Mental stimulation — add to fitness
67efce7d | High Energy Power Walk Energy Drain | Free | No | walking (MERGE → high-energy walk variant) | — | — | 🟡 MERGE | Breed-specific variant of daily walk
svc-PROD-1B4B9807E262 | Agility Training Class | Free | No | PRODUCT — remove | — | — | 🔴 MOVE | Product not service
svc-PROD-6C40202B715E | Puppy Training Course | Free | No | WRONG PILLAR → /learn | — | — | 🔴 MOVE | Training course → /learn
svc-6977d50cf1ba3c3bd6 | Weight Loss Program (4 weeks) | Free | No | fitness (MERGE → duplicate) | — | — | 🟡 MERGE | Duplicate
073943d0 | Large Breed Adventure Walk | Free | No | walking (MERGE → breed-specific walk variant) | — | — | 🟡 MERGE | Breed variant of Dog Walking
8 canonical (green). 71 to merge or move. The 78→8 cleanup removes ~70 duplicates, wrong-pillar entries, and products masquerading as services.
DB COMMAND — run after merging fit services to 8 canonical:
db.services.updateMany( {name:{$in:['Dog Walking - Daily','Dog Walking - Monthly Package','Fitness Assessment & Programme Design','Weight Management Program','Swimming Sessions','Hydrotherapy Sessions','Senior Mobility Planning','Agility Foundation Course']}}, {$set:{pillar:'play',category:'fit'}} )

## NEW Products to Add
New Play Products — 25 Products to Insert ¦ SET pillar='play' on EVERY row ¦ dimension + sub_category required
Product ID | Dimension | Sub-Category (sub_category) | Name | Description | Price (₹) | Mira Pick? | Size Tags | AI Image Prompt | Status
PL-OUT-001 | Play Essentials | outings | Dog Park Survival Kit | Water bottle, collapsible bowl, poop bags, towel, and treat pouch — everything for a park day | 1299 | Yes | All | Realistic product photo: a neat park kit — collapsible bowl, water bottle, treat pouch, towel in a canvas bag, green tones, white background | ADD — pillar='play'
PL-OUT-002 | Play Essentials | outings | Retractable Longline Lead | 10m training lead for recall practice and free-roaming in open spaces — reflective, strong clip | 699 | Yes | All | Realistic product photo: a retractable longline lead in orange and green, neatly coiled, white background | ADD — pillar='play'
PL-OUT-003 | Play Essentials | outings | High-Visibility Safety Vest | Bright reflective vest for evening park runs and dawn walks — keeps your dog visible and safe | 599 | Yes | All | Realistic product photo: a bright orange reflective dog safety vest, minimal clean photo, white background | ADD — pillar='play'
PL-OUT-004 | Play Essentials | outings | Portable Splash Pad | Foldable water pad for garden or park — instant cool-down splash zone for hot days | 1499 | Yes | M/L breeds | Realistic product photo: a round blue portable splash pad for dogs, folded and unfolded views, white background | ADD — pillar='play'
PL-PD-001 | Play Essentials | playdates | Playdate Starter Pack | Rope toy, tug toy, and treat bag — everything needed for a playdate with another dog | 799 | Yes | All | Realistic product photo: a playdate starter kit with rope toy, tug toy, and treat pouch in a green cotton bag, white background | ADD — pillar='play'
PL-PD-002 | Play Essentials | playdates | Interactive Fetch Launcher | Ball launcher for hands-free fetch — extends play time and reduces wrist strain | 1899 | Yes | M/L breeds | Realistic product photo: a green and orange automatic ball launcher for dogs, clean minimal product photo, white background | ADD — pillar='play'
PL-PD-003 | Play Essentials | playdates | Squeaky Ball Set — 3 pack | Bright durable squeaky balls for park and playdate play — high-bounce, non-toxic rubber | 449 | Yes | All | Realistic product photo: a set of 3 colourful squeaky balls in orange, green, and yellow, white background | ADD — pillar='play'
PL-WK-001 | Play Essentials | walking | Hands-Free Running Lead | Waist-belt running lead — keeps your hands free for morning jogs with your dog | 899 | Yes | All | Realistic product photo: a hands-free running lead with waist belt, orange and green, athletic minimal design, white background | ADD — pillar='play'
PL-WK-002 | Play Essentials | walking | Paw Wax & Protective Balm | Protects paws from hot pavements, rough terrain, and sand — travel-size and home-size | 499 | Yes | All | Realistic product photo: a small tin of paw wax balm with paw print lid, natural tones, white background | ADD — pillar='play'
PL-WK-003 | Play Essentials | walking | Walk & Hydration Bottle | All-in-one filtered water bottle with detachable bowl — for walks, runs, and park days | 649 | Yes | All | Realistic product photo: a sleek walk-and-hydrate water bottle with bowl attachment, green and white, white background | ADD — pillar='play'
PL-WK-004 | Play Essentials | walking | Treat Training Pouch | Magnetic-close treat pouch with waste bag holder and key clip — clips to any lead | 349 | Yes | All | Realistic product photo: a neat orange treat training pouch with magnetic closure, clipped to lead, white background | ADD — pillar='play'
PL-FT-001 | Fitness & Training | fitness | Agility Starter Set | 6-piece agility set: hurdles, weave poles, and tunnel — for garden or park use | 2999 | Yes | All | Realistic product photo: a colourful agility set with hurdles, weave poles, and tunnel arranged in a garden, white background | ADD — pillar='play'
PL-FT-002 | Fitness & Training | fitness | Balance Disc for Dogs | Inflatable balance disc for core strength training and coordination — physiotherapy approved | 1299 | Yes | M/L breeds | Realistic product photo: an inflatable balance disc for dogs with non-slip surface, green and orange, white background | ADD — pillar='play'
PL-FT-003 | Fitness & Training | fitness | Pet Weight Scale — Smart | Digital scale that tracks weekly weight — syncs to pet health app, accurate to 50g | 1999 | Yes | All | Realistic product photo: a clean digital pet weight scale with smart display, minimal design, white background | ADD — pillar='play'
PL-FT-004 | Fitness & Training | fitness | Nose Work Kit | Set of 3 hide containers + instruction card for scent work and mental stimulation training | 699 | Yes | All | Realistic product photo: a nose work scent training kit with small containers and illustrated guide card, white background | ADD — pillar='play'
PL-FT-005 | Fitness & Training | fitness | Weighted Exercise Vest — Canine | Low-weight vest for building muscle tone during walks — vet-approved, removable weights | 1799 | Yes | M/L breeds | Realistic product photo: a canine weighted exercise vest in green, removable weight pockets visible, white background | ADD — pillar='play'
PL-FT-006 | Fitness & Training | fitness | Puzzle Feeder — Active Level | High-difficulty puzzle feeder for mental stimulation — makes meals a workout | 899 | Yes | All | Realistic product photo: a multi-level orange and green puzzle feeder for dogs, minimal white background | ADD — pillar='play'
PL-SW-001 | Fitness & Training | swimming | Dog Life Jacket — All Sizes | Safety swim vest with rescue handle — IATA tested, available in XS to XL | 1499 | Yes | All sizes | Realistic product photo: a bright orange dog life jacket with rescue handle, size range shown, white background | ADD — pillar='play'
PL-SW-002 | Fitness & Training | swimming | Post-Swim Microfibre Towel | Super-absorbent quick-dry towel with paw pocket — dries in seconds after swims | 799 | Yes | All | Realistic product photo: a green microfibre dog towel folded with paw pocket detail, clean minimal, white background | ADD — pillar='play'
PL-SW-003 | Fitness & Training | swimming | Pool Ramp for Dogs | Portable pool exit ramp — prevents exhaustion and injury for dogs who love to swim | 2499 | Yes | All | Realistic product photo: a sturdy dog pool exit ramp in green, folded and extended views, white background | ADD — pillar='play'
PL-SW-004 | Fitness & Training | swimming | Waterproof Ear Protectors | Soft silicone ear covers for swimming — protects against ear infections after water play | 399 | Yes | Floppy-eared breeds | Realistic product photo: soft silicone ear covers for dogs, clean minimal white background, green tones | ADD — pillar='play'
PL-SL-001 | Soul Play Products | soul | Playdate Invitation Card Set | Custom illustrated cards with your dog's name and breed — send before a playdate | 299 | Yes | All breeds | Realistic product photo: a set of beautiful illustrated playdate invitation cards with dog breed art and name, cream and green, white background | ADD — pillar='play'
PL-SL-002 | Soul Play Products | soul | Park Day Bandana — Personalised | Breed bandana with 'Park Day with [Name]' embroidery — worn on every outing | 399 | Yes | All breeds | Realistic product photo: a folded personalised bandana with 'Park Day' embroidery and dog name, green and orange, white background | ADD — pillar='play'
PL-SL-003 | Soul Play Products | soul | Fitness Milestone Card | Printed card celebrating a fitness milestone — '100 walks', 'First swim', 'Agility graduate' | 199 | Yes | All breeds | Realistic product photo: a beautiful illustrated milestone certificate card for dogs, gold and green, white background | ADD — pillar='play'
PL-SL-004 | Soul Play Products | soul | Play Passport Journal | Illustrated journal to track every park, beach, trail, and playdate — a map of adventures | 549 | Yes | All breeds | Realistic product photo: a beautiful illustrated dog adventure journal with map and park sticker pages, cream and green, white background | ADD — pillar='play'
Total: 25 new products. All need AI images (prompts in col I). Set pillar='play' on insert.
DIM_ID_TO_CATEGORY — how sub_category maps to the dim panel in PlaySoulPage.jsx
sub_category value | dimension value | API category (JSX) | Dim panel shown | Products | DB insert example
outings | Play Essentials | Play Essentials | Outings & Parks | 4 | {pillar:'play',dimension:'Play Essentials',sub_category:'outings'}
playdates | Play Essentials | Play Essentials | Playdates | 3 | {pillar:'play',dimension:'Play Essentials',sub_category:'playdates'}
walking | Play Essentials | Play Essentials | Dog Walking | 4 | {pillar:'play',dimension:'Play Essentials',sub_category:'walking'}
fitness | Fitness & Training | Fitness & Training | Fitness & Training | 6 | {pillar:'play',dimension:'Fitness & Training',sub_category:'fitness'}
swimming | Fitness & Training | Fitness & Training | Swimming & Hydro | 4 | {pillar:'play',dimension:'Fitness & Training',sub_category:'swimming'}
soul | Soul Play Products | Soul Play Products | Soul Play | 70 | {pillar:'play',dimension:'Soul Play Products',sub_category:'soul'}
⚠️ sub_category MUST be exact lowercase. Wrong value or missing = product invisible in dim panel. Test 1 product first.

## Soul Products (tag existing)
Soul Play Products — 66 Already in DB ¦ Two updateMany() calls = done
Category | Count | Current Pillar | Action | DB Command | Suggested Price | Image Status | Notes
breed-play_bandanas | 33 | unset | SET pillar='play', dimension='Soul Play Products', sub_category='soul' | db.products.updateMany({category:'breed-play_bandanas'},{$set:{pillar:'play',dimension:'Soul Play Products',sub_category:'soul',price:399}}) | ₹399 each | ✅ Cloudinary — uploaded | 33 breeds × 1 bandana. Breed name embroidered. Worn on outings.
breed-playdate_cards | 33 | unset | SET pillar='play', dimension='Soul Play Products', sub_category='soul' | db.products.updateMany({category:'breed-playdate_cards'},{$set:{pillar:'play',dimension:'Soul Play Products',sub_category:'soul',price:299}}) | ₹299 each | ✅ Cloudinary — uploaded | 33 breeds × 1 playdate card. Illustrated with breed. Send before a playdate.
Total: 66 products already in DB. Zero code needed. Two updateMany() calls = play pillar launches with 66 Soul products immediately.

## Bundles (14)
Play Bundles — 14 Bundles ¦ 7 Enjoy + 7 Fit ¦ All new — none exist yet
Bundle ID | Pillar | Sub-Pillar | Name | What's included | Bundle Price (₹) | Original Price (₹) | Savings | Mira Pick? | Watercolour Prompt | Status
BUN-PL-E001 | play | enjoy | Park Day Starter Pack | Dog Park Survival Kit + Squeaky Ball Set (3pk) + Retractable Longline Lead | 1899 | 2447 | 23% off | Yes | Watercolour illustration: a park day starter kit — bag, balls, and lead arranged joyfully, green and orange tones, 16:9 | ADD
BUN-PL-E002 | play | enjoy | Playdate Ready Bundle | Playdate Starter Pack + Interactive Fetch Launcher + Park Day Bandana | 3099 | 3097 | Bundle deal | Yes | Watercolour illustration: playdate essentials — fetch launcher, toys, and personalised bandana, warm park tones, 16:9 | ADD
BUN-PL-E003 | play | enjoy | Weekend Adventure Kit | High-Visibility Safety Vest + Walk & Hydration Bottle + Treat Training Pouch + Paw Wax | 1799 | 2097 | 14% off | Yes | Watercolour illustration: weekend adventure essentials — vest, bottle, pouch in an outdoor setting, 16:9 | ADD
BUN-PL-E004 | play | enjoy | Social Butterfly Bundle | Social Profile Tag + Playdate Invitation Card Set + Park Day Bandana + Treat Pouch | 1199 | 1447 | 17% off | Yes | Watercolour illustration: social dog essentials — tag, invitation cards, and bandana in rose and green, 16:9 | ADD
BUN-PL-E005 | play | enjoy | Beach Day Pack | Portable Splash Pad + Dog Life Jacket + Post-Swim Towel + Paw Wax Balm | 3999 | 4697 | 15% off | Yes | Watercolour illustration: beach day essentials for dogs — splash pad, life jacket, towel on a sunny beach, 16:9 | ADD
BUN-PL-E006 | play | enjoy | Morning Walk Routine | Hands-Free Running Lead + Treat Training Pouch + Walk & Hydration Bottle | 1599 | 1847 | 13% off | Yes | Watercolour illustration: morning walk routine kit — running lead, treat pouch, water bottle at golden hour, 16:9 | ADD
BUN-PL-E007 | play | enjoy | Play Passport Bundle | Play Passport Journal + Fitness Milestone Card + Playdate Invitation Card Set | 899 | 1047 | 14% off | Yes | Watercolour illustration: a dog's adventure journal, milestone cards, and invitation set — memories made beautiful, 16:9 | ADD
BUN-PL-F001 | play | fit | Agility Starter Kit | Agility Starter Set + Balance Disc for Dogs + Treat Training Pouch | 3799 | 4347 | 13% off | Yes | Watercolour illustration: agility kit — hurdles, balance disc, and treat pouch in an energetic garden setting, 16:9 | ADD
BUN-PL-F002 | play | fit | Weight Management Programme Pack | Pet Weight Scale (Smart) + Fitness Assessment service credit + Puzzle Feeder | 3499 | 4797 | 27% off | Yes | Watercolour illustration: weight management kit — scale, puzzle feeder, and assessment card in clean green tones, 16:9 | ADD
BUN-PL-F003 | play | fit | Swimming Starter Bundle | Dog Life Jacket + Post-Swim Microfibre Towel + Waterproof Ear Protectors + Pool Ramp | 4699 | 5197 | 10% off | Yes | Watercolour illustration: swimming starter kit — life jacket, towel, ear covers, and ramp in aqua and green, 16:9 | ADD
BUN-PL-F004 | play | fit | Senior Active Living Bundle | Senior Mobility service credit + Balance Disc + Paw Wax + Post-Swim Towel | 2999 | 3997 | 25% off | Yes | Watercolour illustration: senior dog active living kit — balance disc, balm, and towel in soft warm tones, 16:9 | ADD
BUN-PL-F005 | play | fit | Nose Work & Mental Fitness Kit | Nose Work Kit + Puzzle Feeder + Play Passport Journal | 1699 | 2147 | 21% off | Yes | Watercolour illustration: mental fitness kit — scent containers, puzzle feeder, and journal in warm sage tones, 16:9 | ADD
BUN-PL-F006 | play | fit | High-Energy Breed Bundle | Weighted Exercise Vest + Agility Starter Set + Hands-Free Running Lead | 5099 | 5697 | 10% off | Yes | Watercolour illustration: high-energy breed kit — weighted vest, agility set, and running lead in bold orange and green, 16:9 | ADD
BUN-PL-F007 | play | fit | Puppy Play & Grow Bundle | Squeaky Ball Set + Nose Work Kit + Balance Disc + Play Passport Journal | 2799 | 3447 | 19% off | Yes | Watercolour illustration: puppy play and grow kit — bright balls, scent game, balance disc in playful colours, 16:9 | ADD
14 bundles: 7 Enjoy (green) + 7 Fit (orange). All new — none exist in DB. Generate watercolour images using prompts in col J.

## Guided Play Paths (6)
Guided Play Paths — 6 Paths ¦ 4-step PathFlowModal ¦ POST /api/concierge/play-path
Path ID | Title | Badge | Accent | Step 1 | Step 2 | Step 3 | Step 4 | Notes
park_day | Park & Playdate Path | Mira Pick | #2D6A4F | Energy level? (single: Calm & relaxed / Moderately active / Very high energy / Varies by day) | What kind of park? (single: Off-lead dog park / Structured play area / Hiking trail / Beach / Any) | Who's coming? (single: Just us / With another dog / Group playdate / New dog meeting for first time) | What to bring? (multi: Water & bowl, Treats, Longline lead, Fetch toy, Poop bags, First aid, All of above) | { petId, pathId:'park_day', selections } → POST /api/concierge/play-path. Ends with park recommendations near user.
dog_walking | Dog Walking Path | Daily routine | #E76F51 | Walk style? (single: Casual sniff walk / Brisk exercise walk / Running / Training walk with commands) | How often? (single: Daily / Every other day / Few times a week / Need a walker to help) | Any challenges? (multi: Pulls on lead, Reactive to other dogs, Scared of traffic, Doesn't want to walk, Gets too excited) | What support? (single: Self-walk tips / Book a professional walker / Both — I need a plan) | { petId, pathId:'dog_walking', selections } → POST /api/concierge/play-path
fitness_plan | Fitness & Training Path | Mira builds plan | #1B4332 | Fitness goal? (single: General health & fitness / Weight loss / Build muscle & stamina / Senior mobility / Agility sport) | Current activity level? (single: Barely any exercise / Short walks only / Moderate activity / Very active already) | Any health conditions? (single: None / Joint issues / Overweight / Post-surgery / Senior dog) | Training interest? (multi: Agility course, Nose work, Balance training, Weighted walks, Swimming, Treadmill, All) | { petId, pathId:'fitness_plan', selections } → POST /api/concierge/play-path. Mira builds personalised 4-week plan.
swimming_hydro | Swimming & Hydrotherapy Path | Splashes & heals | #1565C0 | Swim experience? (single: Never swum before / Tried once or twice / Loves water / Professional hydrotherapy needed) | Why swimming? (single: Fun & fitness / Weight management / Joint recovery / Post-surgery rehab / Just to try it) | Safety check? (single: Has life jacket / Needs one / Not sure about water confidence yet) | Session type? (single: Open water / Private pool session / Hydrotherapy centre / Home paddling pool) | { petId, pathId:'swimming_hydro', selections } → POST /api/concierge/play-path
adventure_day | Weekend Adventure Path | Go explore | #C9973A | Adventure type? (single: Beach day / Hill hike / Forest trail / Lake & water / City exploration / Camping) | Distance? (single: Short (under 3km) / Medium (3–8km) / Long (8km+) / Let Mira decide by breed) | Who's coming? (single: Just us / Partner / Kids too / Other dogs / Full group) | What to prepare? (multi: Route planning, Emergency vet en route, Pet-friendly cafe stops, Activity kit, First aid, All) | { petId, pathId:'adventure_day', selections } → POST /api/concierge/play-path. Ends with Mira-curated route.
social_life | Social & Events Path | Make friends | #9B59B6 | Socialisation experience? (single: Never socialised properly / Limited experience / Good with known dogs / Fully social) | What kind of social? (single: One-on-one playdate / Small group / Dog park meetup / Breed-specific event / Pet-friendly event) | Social goal? (single: Build confidence / Make dog friends / Exercise through play / Find a regular playmate) | Concerns? (multi: Dog is reactive, Dog is shy, Owner is nervous, Finding right match, All good — just want a plan) | { petId, pathId:'social_life', selections } → POST /api/concierge/play-path

## Aditya Checklist
Aditya — Play Pillar Action Checklist ¦ In Priority Order
# | Priority | Action | Reference | DB Command / Notes | Done
1 | 🔴 Do first | Tag 33 breed play bandanas as play | Soul Products sheet | db.products.updateMany({category:'breed-play_bandanas'},{$set:{pillar:'play',dimension:'Soul Play Products',sub_category:'soul',price:399}}) | ☐
2 | 🔴 Do first | Tag 33 breed playdate cards as play | Soul Products sheet | db.products.updateMany({category:'breed-playdate_cards'},{$set:{pillar:'play',dimension:'Soul Play Products',sub_category:'soul',price:299}}) | ☐
3 | 🔴 Do first | Move 8 wrong-pillar services out of Fit | Fit Services sheet — red rows | Heartworm/Flea→care ¦ Training→learn ¦ Emergency transport→emergency ¦ Passport→go ¦ Products→delete from services | ☐
4 | 🔴 Do first | Move 3 wrong-pillar services out of Enjoy | Enjoy Services sheet — red rows | Heartworm×2→care ¦ Flea→care ¦ Product services→delete | ☐
5 | 🔴 Do first | Merge enjoy duplicates → 8 canonical | Enjoy Services sheet — yellow rows | Keep the 8 green rows. Copy unique descriptions from yellow. Delete duplicates. | ☐
6 | 🔴 Do first | Merge fit duplicates → 8 canonical | Fit Services sheet — yellow rows | Keep 8 green rows. ~62 duplicates/wrong-pillar to clean. Set pillar='play' on all 16 canonical. | ☐
7 | 🟡 This week | Insert 25 new play products | NEW Products to Add sheet | All with pillar='play', dimension and sub_category as shown. Generate AI images from col I prompts. | ☐
8 | 🟡 This week | Create 14 play bundles in DB | Bundles sheet | 7 enjoy + 7 fit. Set pillar='play', category='enjoy' or 'fit'. Generate watercolour images. | ☐
9 | 🟡 This week | Drop 7 JSX files into codebase | PlaySoulPage.jsx + 6 components → /components/play/ | Same drop-in pattern as /go and /care | ☐
10 | 🟡 This week | Add route: /play | PlaySoulPage.jsx | <Route path='/play' element={<PlaySoulPage/>}/> | ☐
11 | 🟡 This week | Remove /enjoy and /fit from nav | Nav component | Both replaced by single /play entry | ☐
12 | 🟡 This week | Wire play-booking endpoint | PlaySoulPage.jsx — 8 booking flows | POST /api/concierge/play-booking body: {petId, serviceId, steps} | ☐
13 | 🟡 This week | Wire play-path endpoint | GuidedPlayPaths.jsx | POST /api/concierge/play-path body: {petId, pathId, selections} | ☐
14 | 🟡 This week | Wire play-intake endpoint | PlayConciergeModal.jsx | POST /api/concierge/play-intake body: {petId, occasion, date, notes} | ☐
15 | 🟢 Later | Generate watercolour service images | Enjoy Services sheet col G + Fit Services col G | 16 canonical services need watercolour illustrations | ☐
16 | 🟢 Later | Generate AI product images for 25 new products | NEW Products sheet col I | All prompts ready. Upload to Cloudinary. | ☐
17 | 🟢 Later | Add PetFriendlyPlaces for /play | Same pattern as PetFriendlyStays for /go | Search: 'pet friendly park' + 'dog cafe' — same Google Places textSearch pattern | ☐
18 | 🟢 Later | Set energy_level + sport flags on services | All 16 canonical play services | energy_level: low/medium/high + sport: agility/swimming/walking/running — helps Mira filter by soul profile | ☐
19 | 🔴 Do first | SET pillar='play' on all 16 canonical services after merging | See DB commands at bottom of Enjoy Services + Fit Services sheets | db.services.updateMany({name:{$in:['Pet Parks Discovery','Playdate Coordination','Pet Events & Experiences','Socialisation Planning','Weekend Outing Planning','Breed-Specific Playdate','Dog Beach Day','Social Calendar Management','Dog Walking - Daily','Dog Walking - Monthly Package','Fitness Assessment & Programme Design','Weight Management Program','Swimming Sessions','Hydrotherapy Sessions','Senior Mobility Planning','Agility Foundation Course']}},{$set:{pillar:'play'}}) | ☐
20 | 🔴 Do first | Insert ALL 25 new products with 3 mandatory fields: pillar='play' + dimension + sub_category | NEW Products sheet — col 2 = dimension, col 3 = sub_category. See mapping table below the products. | All 3 fields required. Example: {pillar:'play', dimension:'Play Essentials', sub_category:'outings', name:'Dog Park Survival Kit', price:1299}. Missing even one = product won't show in dim panel. | ☐
21 | 🔴 Do first | sub_category must be EXACT lowercase. 6 valid values only. | NEW Products sheet — mapping table shows all 6 valid sub_category values | Valid: outings ¦ playdates ¦ walking ¦ fitness ¦ swimming ¦ soul. Any typo or capitalisation = product invisible. Test with 1 product first before bulk insert. | ☐
22 | 🟡 This week | Remove /enjoy AND /fit from nav — replace both with single /play entry | Nav component — this merges both old pillars into one | Both /enjoy and /fit routes should 301-redirect to /play. The PlaySoulPage serves both Enjoy and Fit content. | ☐